## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
|  |  | GPU Non-availability for YOLO model training | s2 | Aarya Yogesh Pakhale | Logical | Used Colab to train | 2024-11-15 | Closed
|  |  | Sort module not having class id | s3 | Aarya Yogesh Pakhale | Logical | Used the earlier Yolo Model | 2024-12-10 | Closed
|  |  | Missing Detections in some frames | s4 | Aarya Yogesh Pakhale | User Interface | Interpolated the bounding boxes | 2024-12-21 | Closed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others